## Sheet1
Research Compliance Services Continuous Quality Improvement Action Plan
Note: RCS Leadership = RCS Director and Asst. Director; IRB Leadership = IRB Chair and Co-Chairs; RTS=Research Technology Services, FAVP= Faculty Associate Vice President for Research
| Responsible Party | Target Start Date | Target Completion Date
Actions |  |  |  | Resources
Priority Area 1: Operational Metrics Data & Reporting
Establish priorities and timeline for operational metrics data project | AVP-Research Integrity & RCS Director | n/a | Completed 10/23 | Time, Staffing
Establish Project Team for operational metrics data project; review deliverables and meet routinely | RCS Director & RTS | Started 10/2023 | Ongoing | Time, Staffing
Project Team creates breakdown of priority areas | RCS Director /Project Team | 2023-10-01 | 2024-07-01 | Time, Staffing, System/Tech
Project Team refines portfolio of reports for internal (RCS) and external (UO) use; evaluate; refine and revise | Project Team | 2023-10-01 | Ongoing | Time, Staffing, System/Tech
Routine review of reports by the Director and FAVP to enhance deliverables; review data, analyze and interpret; refine | RCS Director, FAVP & AVP-Research Integrity | 2024-03-01 | Ongoing | Time, Staffing, System/Tech
Project team will continue evaluation and refinement including integrating different categories of submissions (e.g., student/faculty, funded/funded, number of other submissions) to explore patterns and themes that may inform outreach and education efforts. | Project Team | 2024-07-01 | 7/2024 & Ongoing | Time, Staffing, System/Tech
Generate standard reports at frequency intervals based on data type (e.g., quarterly report meetings beginning in July 2024, annually); use data internally (e.g., RCS Leadership and OVPRI Leadership) and share externally (e.g., research community) | Project Team/RCS Leadership | 2023-10-01 | 7/2024 & Ongoing | Time, Staffing, System/Tech
Use data from project to explore workload and bandwidth within RCS | RCS Leadership | 2024-05-01 | 7/2024 & Ongoing | Time, Staffing, Expertise, System/Tech
Use data from project to explore turnaround times; review with set targets with ongoing monitoring | RCS Leadership | 2024-03-01 | 6/2024 & Ongoing | Time, Staffing, Expertise, System/Tech
Incorporate discussions about expectations for timelines and other benchmarks in weekly operations meeting of current submission volume to maximize effectiveness of prioritization | RCS Director | Already Ongoing | Refine by 6/2024 | Time, Staffing, Expertise
Review Association for the Accreditation of Human Research Protection Programs (AAHRPP) Data for target comparisons and benchmarking | RCS Director | 2024-05-01 | 7/2024 & Ongoing | Time, Staffing, Expertise
Review publicly available metrics data from outside institutions for target comparisons and benchmarking | RCS Director | 2024-05-01 | 7/2024 & Ongoing | Time, Staffing, Expertise
Build and use internal report to routinely identify studies with multiple instances of “clarifications requested;” RCS Director/Asst. Director retrospectively review and address/provide feedback to staff and research community | RCS Leadership | 2024-04-01 | Ongoing | Time, Staffing, Expertise
To promote consistency and minimize clarifications whenever possible, new issues/concerns identified in previously approved protocols will be discussed with RCS leadership and/or the IRB prior to requesting changes. | RCS Staff & Leadership | Already Ongoing | n/a | Time, Staffing, System/Tech
Publish Dashboard of relevant data for IRB users, including the ability to view data about protocols & timelines on a unit-specific basis | RCS & RTS | 2025-06-01 | 2025-06-01 | System/Tech
Priority Area 2: RCS Internal Quality Assurance
Implementation of “red, yellow, green” categories in team operations meeting to triage protocols and define turn around targets and other benchmarks | RCS Staff & Leadership | 2024-04-01 | Ongoing | Time, Staffing, Expertise
Define rush designation on protocols-intake process and operations log | RCS Staff & Leadership | Already Ongoing | n/a | Time, Staffing, Expertise
Review of internal resources (e.g., staffing, funds dedicated for RAP customizations); comparison with data and target timelines and deliverables | RCS Leadership, Project Team (RCS/RTS) | Already Ongoing | 2024-10-01 | Time, Staffing, Expertise, System/Tech
Refine and expand phase 3 of CQI based on priority area 3 (process and procedures), priority area 4 (communication and outreach) and priority area 5 (training and education) | RCS Leadership | Already Ongoing | Refine Phase 3 by 8/2024 | Time, Staffing, Expertise, System/Tech, Comms
RCS continues CQI work-building/enhancing/reviewing priority area 3 (process and procedures), priority area 4 (communication and outreach) and priority area 5 (training and education). For example, RCS will refine internal guidance and procedures; continue to conduct training for new and existing RCS staff; and engage in continuing education and professional development in HSR and communications | RCS Staff &Leadership | Already Ongoing | 8/2024 & Ongoing | Time, Staffing, Expertise, System/Tech, Comms
RCS Director/Asst. Director will routinely review sampling of protocol reviews to monitor, oversee, and identify areas of improvement (consistency, efficiency, etc.), training and outreach needs. These reviews will include a sampling of clarifications requested in protocols already approved and protocols with multiple instances of clarifications required. | RCS Leadership | 2024-04-01 | Ongoing | Time, Staffing, Expertise, System/Tech
Priority Area 3: Process & Procedures
RCS leadership will assess exempt and expedited review procedures for expediency, compliance, quality and clarity. | RCS Leadership | Already Ongoing | Ongoing | Time, Staffing, Expertise
RCS leadership will continue to assess communication and outreach procedures for expediency, compliance, and customer service. | RCS Leadership | Already Ongoing | Ongoing | Time, Staffing, Expertise
RCS will screen full committee reviewer materials in advance of IRB Meetings; prioritize researcher changes in advance if received in timely manner | RCS Staff & Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
RCS will monitor and adapt process for deadlines; researcher requests, committee deadlines etc. | RCS Staff & Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
RCS will streamline procedures to improve full board committee efficiency during meetings | RCS Staff & Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
Evaluate IRB committee membership annually; recruitment and retention among identified key departments (e.g., child rep., medical expertise) | RCS Leadership/IRB Leadership | Summer 2024 | Fall, Annually | Time, Staffing, Expertise
RCS will continue facilitation of two fully convened IRBs per month to ensure full board studies are reviewed in a timely manner | RCS Staff & Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
Priority Area 4: Communication & Outreach
Establish and implement HSR Advisory Committee (HRAC) comprised of faculty from identified departments to provide guidance and feedback between RCS and research community | RCS, OVRPI FAVP/ Faculty Representatives | Spring 2024 | Ongoing | Time, Staffing, Expertise
Liaison Group: Offer units that are key (frequent) IRB users the opportunity to identify a representative such as a project coordinator, research assistant, Department Grant Administrator, etc. to serve as members of a Liaison Group; Liaison Group to work closely with RCS to advertise and broaden knowledge in priority areas, socialize changes, and undergo additional outreach/training; use Liaison Group to obtain feedback. | RCS Leadership, Department., Departmental Reps. | 2025-05-01 | 9/2024 & Ongoing | Time, Staffing, Expertise
Implement an Annual Customer Service Survey; HRAC communicate results to research community | HRAC | TBD | Spring, annually | Time, Staffing, Expertise, System/Tech, Comms
Administer RCS Satisfaction and accessibility survey, with link available in key communications and emails from RCS; implementation of a “suggestion box” link advertised and available on RCS website; survey is distinct for its brevity and real-time collection of feedback; communicate results to HRAC | RCS Leadership | Already Ongoing | Ongoing | Time, Staffing, Expertise, System/Tech, Comms
Continue RCS Website updates as new materials and guidance are developed | RCS Staff and Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech, Comms
Establish and host RCS Virtual Office Hours, twice weekly | RCS Staff | 2024-03-01 | Ongoing | Time, Staffing, Expertise, System/Tech, Comms
RCS continue Pre-Review to address modifications needed to secure approval (prevent table/defer or disapproval) | RCS Staff | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
RCS to highlight fully convened IRB review process with “heavy user” researcher to educate/facilitate understanding/normalize expectations | RCS Staff & Leadership | Fall 2024 | Fall 2024 | Time, Staffing, Expertise
RCS to continue offering RCS Director contact information for researchers to have an avenue to express concerns/RCS Director to facilitate discussions and resolutions; outreach will also highlight process to respond with information differing from what is requested by RCS staff or the IRB. | RCS Leadership | Already Ongoing | Ongoing | Comms
Targeted outreach and connection between RCS leadership and key departments (insight from Liaison groups and HRAC as needed); RCS Director hosts quarterly meeting with key dept leaders/reps | RCS Leadership | Already Ongoing | Refine by Fall 2024 | Time, Staffing, Expertise, Comms
Targeted education and outreach on emerging topical areas to enhance understanding and opportunity for feedback from research community. These topics may emerge from questions, complaints, RCS staff feedback and survey response. | RCS Staff & Leadership | Already Ongoing, refine for Fall 2024 | Ongoing | Time, Staffing, Expertise, System/Tech, Comms
Email “Blasts” to advertise education, guidance, enhancements, available resources, etc. (partner with OVPRI communications, use DGA group, Liaison Groups, Frontline, etc.) | RCS Staff & Leadership, SPS, Comms, Depts. | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech, Comms
Priority Area 5: Training & Education
IRB Members: Evaluation of training needs; develop and implement training plan | RCS Leadership/ | 2024-04-01 | 2024-06-01 | Time, Staffing, Expertise
IRB Leadership
IRB Members: Continue incoming member training and orientation; special emphasis on regulatory areas requiring specially designated members | RCS Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
IRB Members: Develop and implement continued education; host annual refresher training for all members | RCS Leadership | Already Ongoing | Fall 2024 & Annual Event each Fall | Time, Staffing, Expertise, System/Tech
IRB Members: RCS to provide guidance on regulatory paths for meeting approval criteria (avoid table/defer or disapproval) | RCS Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
Researchers: Additional educational offerings based on survey feedback, liaison input and frequent questions that come up during office hours, emails to RCS, and reviews. Offerings may include multiple learning modalities to be offered including short video clips, recordings of hosted trainings, guidance documents and tools, specific topical educational pieces, FAQs, and more based on feedback. | RCS Staff & Leadership | Already Ongoing | 3/2024 & Ongoing | Time, Staffing, Expertise, System/Tech (e.g., video creation)
RCS Staff: Targeted training of staff w/sampling of revisions requested reviewed quarterly for internal improvement/staff education | RCS Leadership | Already Ongoing | Ongoing & refine by 6/2024 | Time, Staffing, Expertise, System/Tech
RCS Staff: Develop and/or advertise available guidance in priority topical areas, including research with multiple sub-studies | RCS Staff & Leadership | Already Ongoing | Ongoing & new by 9/2024 | Time, Staffing, Expertise, System/Tech, Comms
RCS Staff: Internal coaching for balanced approach to ensure regulatory compliance, best practices for HSR protections in existing research; how to address errors or inconsistencies from previous reviews; communications coaching; Coaching can be enhanced by data developed from reports described in priority area 1 (Operational Metrics Data & Reporting) | RCS Director/RCS Leadership | Already Ongoing | n/a | Time, Staffing, Expertise, System/Tech
RCS/OVPRI Communications-revamp of RCS webpages | Project Team (RCS/Comms) | TBD/needs scheduled |  | Time, Staffing, Expertise, System/Tech, Comms